DEPARTMENT OF HOMELAND SECURITY

SCIENCE AND TECHNOLOGY DIRECTORATE

Project Management Plan (PMP)

Port and Coastal Surveillance Improvement

DRAFT

7 FEBRUARY 2013

PMP Approvals:

_____________________________	____________

Project Manager	Date

_____________________________	____________

Division Director	Date

Record of Changes

| Version | Date | Figure # or Section # | A/M/D* | Description of Change / Rationale |
| --- | --- | --- | --- | --- |
| DRAFT | 7 FEB 2013 |  |  | Updated Draft of FY13 PMP |

* A-Added, M-Modified, D-Deleted

Contents

1.	Project Summary	1

1.1	Background and Purpose	1

1.2	Customer(s)	1

1.3	Deliverables/Products	1

1.4	Transition Plan	2

1.5	Schedule and Budget Summary	2

1.6	Project Organization	4

1.6.1	Project Personnel	4

1.6.2	Internal Structure	4

1.7	Benefits to S&T	4

1.7.1	New Capabilities / Technology	5

1.7.2	New Intellectual Property	5

1.7.1	Other Benefits	5

1.8	Assumptions	6

2.	Requirements	6

2.1	Requirements Management Plan	6

2.2	Customer Engagement	6

2.3	Customer Requirements	6

2.4	Key Performance Parameters	6

2.5	Other Metrics	7

3.	Technology and Innovation	8

3.1	Core Technology	8

3.2	Technology Foraging	8

3.3	Technical Approach	8

3.3.1	Analysis of Alternatives	8

3.3.2	Preferred Alternative	8

3.3.3	Technical Risks	9

4.	Project Management	10

4.1	Acquisition Management	10

4.1.1	Acquisition Strategy	10

4.1.2	Potential Vendors	10

4.2	Scope Management	10

4.2.1	Work Breakdown Structure	10

4.2.2	Scope Control Plan	10

4.3	Schedule Management	10

4.3.1	Milestones/Deliverables	11

4.3.2	Schedule Control Plan	11

4.4	Cost Management	11

4.4.1	Cost Estimate	11

4.4.2	Cost Baseline	11

4.4.3	Cost Control Plan	12

4.5	Status Reporting	12

5.	Risk Management	13

5.1	Risk Management Plan	13

5.2	Risk Identification and Assessment	13

# Project Summary

## Background and Purpose

Purpose of PCSI is to provide an enhanced Maritime Situational Awareness by enabling affordable, persistent, pervasive surveillance for law enforcement organizations.  Currently, DHS components suffer from various capability gaps which fail to provide concise, dynamic large scale views of their operating maritime environment.  The result of this is a degraded situational awareness and inefficient use of personnel and resources.  The inherent accessibility of coastlines and harbors, the large volume of commercial and private traffic and the lack of policy to mandate a required tracking feature to all vessels (large and small) makes the security of coastal environs one of the highest priority strategic security goals for DHS.  The benefits of PCSI includes vastly improved coordination amongst DoD/DHS assets and greater detection and interdiction capabilities for small vessel targets.  Small Dark Vessel (SDV), is a sister program within Borders & Maritime that will benefit from PCSI, as both programs support the goal of interception of small vessels.  In the case of SDV, PCSI technologies can be used to help detect SDVs.  The next evolution of PCSI is CSS (Coast Surveillance System).  CSS will incorporate the advancements from PCSI into its satellite information network and UAS resources for a greater operating picture of the maritime environment.  PCSI will give DHS S&T a powerful new tool that can be provided to other DHS component agencies in need of a broad intelligence package providing up-to-date, dynamic information for its deployed operators, along with historical vessel tracking data to help plan future operations.

## Customer(s)

Primary customer is CBP OAM & OTIA, and USCG.  The highest level customer participation is at the Flag/SES HQ level.  Customer support included use of facilities, resources, and people while developing and testing technologies.  CBP embedded personnel in their existing systems and operated on missions and in controlled testing environments.  USCG has provided technical support personnel for OMS (Open Mongoose System, a declassified version of a DoD program known as Sealink Advanced Analysis, which provides vessel tracking data for maritime missions) deployment in PCSI.  CBP and USCG are both conducting maritime-oriented security missions.  An operational PCSI system will greatly contribute to their operational mission postures by providing OMS track service, a new SIMON information integration platform, and new vessel track data sources such as OPT radar buoy, Smart Chart AIS, and NOAA’s HF radar.

## Deliverables/Products

The AMOC Technology Enhancement Demonstration took place in FY2013, Q1.  It consisted of 4 phases.   In October 2012, the systems engineering team began Phase I of OMS deployment.  Phase I is Bench Integration.  The SE team coordinated the physical and network integration plan with respective SMEs at LA/LB test bed and AMOC.  Phase 2 was On-Location Deployment and Integration.  Physical and network integration activities will be conducted within the LA/LB and AMOC command centers.  Phase 3 is Continued Integration, Improvement, and Demo Preparation.  A single, federated system capability with an enhanced SA among the geographically separated command centers will be created.  Phase 4 is Final Preparation and Setup, which consisted final demonstration at the AMOC command center.

In FY 2013, BMD plans to employ PCSI in conjunction with the DHS/DoD JCTD-developed capability entitled Coalition Tactical Awareness and Response (CTAR, and Deep Sea Web JCTD.Other deliverables in FY13 will be the fusion of “other” data sources in Open Mongoose System.

Client satisfaction will be determined by operational milestone accomplishment and impact on current missions.

## Transition Plan

All technology development and demonstrations to be conducted under this port and coastal surveillance improvement project and resulting coastal surveillance system will provide DHS Components with cost and performance data for a more effective port and coastal surveillance system. Future acquisition programs including but not limited to the USCG’s Command 21/InterAgency Operations Center (IOC) Program and affiliated USCG Command and Control (C2) Programs (e.g. USCG Rescue 21 Program and National Automatic Identification System Program) and CBP Air and Marine Operations System Phase B Modernization Effort as well as the NOAA IOOS System (e.g. HF Radar Program).  The technology solutions will address numerous key Homeland Security maritime risks including detection and tracking and alerting operators of anomalous behaviors by both large and small vessels.

In FY2013, OMS will be deployed to LA/LB testbed for operational evaluation. Operational evaluation of OMS has already begun in AMOC following its deployment in Q1FY13.

Performers have been integrated into CBP operations to observe existing systems and user \          capabilities in mission environments.

## Schedule and Budget Summary

Figure 1: High-Level Milestone and Budget Summary

| Project Activities | FY13 | FY14 | FY15 |
| --- | --- | --- | --- |
| Allocated Funding | $3.5 | $2.0 | $0.0 |
| Demos |  |  |  |
| Deliverables/Transitions |  |  |  |

| Funding Source | FY13 | FY14 | FY15 | Total |
| --- | --- | --- | --- | --- |
| Internal (S&T) | 3.5 | 2.0 | 0.0 | 5.5 |

Figure 2: Budget Source Summary

## Project Organization

BMD Internal Staff Organization

| Name | Organization | Title/Role | Email | Phone |
| --- | --- | --- | --- | --- |
| ## Thomas Tomaiko | ## DHS S&T | ## Program Manager | ## Thomas.tomaiko@hq.dhs.gov | ## 202-254-5681 |
| ## Gerald Bowe | ## DHS S&T | ## Operations Manger | ## gbowe@caci.com | ## 561-389-8103 |
| ## Kim Babcock | ## USCG | ## Transition Manager | ## Kim.r.babcock@uscg.mil | ## 860-271-2719 |
| ## Shawn McDonald | ## DHS S&T (NSWC) | ## Technology Manager | ## Shawn.mcdonald1@navy.mil | ## 540-254-5879 |
| ## Michael Ciccarello | ## DHS S&T | ## SETA Support | ## michael.ciccarello@associates.hq.dhs.gov | ## 202-254-6088 |

Performer Organization

| Organization | POC |
| --- | --- |
| ## Navy Surface Warfare Center | ## Gerald Bowe |
| ## SRI | ## Paul Morrisseau |
| ## National Research Laboratory | ## Annie Lum, Jay Middour |
| ## ARL UT | ## Gary Wilson |
| ## SPAWAR | ## David Pollock |

Figure 3: Project Personnel

### Internal Structure

Refer to section 1.6.

## Benefits to S&T

PCSI is built off existing systems and technologies, providing massive R&D savings to DHS S&T.  For example, the Open Mongoose System is based off a 7 year, $100 million dollar classified system called Sealink Advance Analysis.  Through cooperation with DoD, Sealink was developed into an unclassified system providing actionable intelligence to maritime law enforcement agencies.  The Maritime Security Technology Platform (MSTP and the SIMON platform is built upon), is designed to be a rapid integration enabling technology for a federation of data between and amongst multiple disparate enterprises or networks.

This multi-input intelligence engine provides a critical technology to fulfill identified capability gaps which hinders law enforcement operations.  This is crucial when facing multi-faceted and evolving homeland security threats.

1.7.1  New Capabilities / Technology

Refer to 1.7

### 1.7.2 New Intellectual Property

.

No new intellectual property is expected to be produced by this effort.

### 1.7.3 Other Benefits

No additional benefits are expected to be produced by this effort.

## Assumptions

.

Project is based on the assumption that criminal and terrorist organizations will continue to exploit maritime security vulnerabilities using uncooperative vessels, e.g, pangas, in order to penetrate coastal areas to drop off illicit cargo, illegal immigrants, etc.  Also being executed under the assumption that the client operations parameters will remain the same during Initial Operating Capability and beyond.

# Requirements

## Requirements Management Plan

The ops manager has the responsibility maintaining the Requirements Management Plan.  He will use the RMP to document the necessary information from definition of baseline criteria, development, transition, and delivery.  Intended audience will be the project manager, project team, project sponsor, and client customers/sponsors.  Requirements are collected from an analysis of specific threat capabilities that need to be countered and client gap vulnerabilities (from a maritime interdiction mission context).  They are tracked through JMT development and validated through modeling and simulation studies and prototype implementation analysis.  PCSI requirements are approved by the client at HQ level.  Testing is conducted by the performers.  Sharepoint and Excel is used to track project requirements.

## Customer Engagement

The PM meets with various CBP client representatives on a weekly basis, especially with those from the Air and Marine Operations Center.  The PMP keeps the clients actively engaged by highlighting responsibilities of the performers and details the schedule of milestones that the client can expect.

## Customer Requirements

Customer requires a radar capability enhanced for harbor and 0-12 nautical miles to detect, track, and identify vessels in ports and coastal regions.  This will assist in addressing the problem of detecting non-cooperative small vessels.  Customers that will benefit from this capability are USCG, CBP, and ICE.  Leadership at headquarters levels of these organizations have stated a need for this capability.  The customer’s requirements and purpose for PCSI is to detect and track non-cooperative small vessels which will lead to greater resource alignment with mission needs.   Customer requirements are sufficiently clear and reinforced through integration of DHS S&T personnel in client’s operational missions and briefings.  Customer vulnerabilities and requirements originate from FY 2007 Capstone process and re-validated in FY 2008 Maritime Security Capstone Integrated Process Team (IPT) document.

## Key Performance Parameters

| # | Key Performance Parameters (KPP) | Baseline |  |
| --- | --- | --- | --- |
|  |  | Threshold | Objective |
| KPP #1 | Net-ready: The system must support net-centric military operations. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The system must continuously provide survivable, interoperable, secure, and operationally effective information exchanges to enable a net-centric military capability. | The system will be developed so that it aims to support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system will be developed so that it can be later modified to meet technical requirements for transition to Net-centric military operations. | The system will be developed so that it aims to support execution of all operational activities identified in the applicable joint and system integrated architectures and the system will be developed so that it can be later modified to meet technical requirements for Net-centric military operations. |
| KPP #2 | Collaborative Information Environment – The system shall provide a CIE created by a suite of integrated, web-enabled applications. These applications shall be integrated through the use of existing service registries, existing service catalogs, and shall allow services to self-register. The following subsections will further describe the CIE capability. | CIE contains multiple sub-thresholds. Refer to CONOP JMT TIER 1 KPP | CIE contains multiple sub-thresholds. Refer to CONOP JMT TIER 1 KPP |
| KPP#3 | Common Operational Picture (COP) The system shall integrate, display, and process data accurately as available in the integrated area(s) of responsibility (AOR).. | (1) Display capabilities for processed data in map and tabular views for tracks, alerts and events. (2) Control capabilities for cameras and videos. | (1) Display capabilities for processed data in map and tabular views for tracks, alerts and events. (2) Control capabilities for cameras and videos |
| KPP#4 | The system shall have a capability to process and display all target information in near real time on an unclassified C2 system. | Unclassified | Classified |

Figure 4: Key Performance Parameters

## Other Metrics

None.

# Technology and Innovation

## Core Technology

Recent core technology deliverables for FY 2012 include the SRI SIMON-based MDAS and the NRL Open Mongoose System.  Other new solutions include new multi-INT Persistent Wide Area Suveillance/Precision Geo-Location Capabilities.  This WAS (Wide Area Surveillance) capability is comprised of:

- algorithims to enable ship detection and generation of reports using NOAA HFR, DoD aerostat (air) radars, and shipboard commercial navigation radars.

- Multi-INT buoy extension with power generation

- Mobile terminal to produce timely ship detection service using commercial SAR/EO satellites

- Develop buoy-based and sea-floor acoustic detection technology

- Develop a 3G/4G cellular based smart phone application and new Class E AIS standard.

Existing technology and infrastructure was foraged for PCSI..

## Technology Foraging

Extensive tech foraging was conducted in the PM office.  PCSI project formulation determined the sensor and surveillance technology shortfalls in the project.  The technology shortfalls were also consistent with the identified technology deficiencies associated with key Homeland Security maritime mission risks.

Performers selected by the PM office analyzed available risk assessments from DHS components, key maritime risk scenario categories, and dominant risk attack modes.  Subject Matter Experts (SMEs) identified what activities are associated with detect, decide, engage, and defeat actions and the roles of those activities.  Research was conducted to see what solution technology was available to answer these vulnerabilities.

## Technical Approach

### Analysis of Alternatives

During the Material Solutions Analysis, customer requirements were based upon joint mission threads and the evolving threat environment/capability gaps facing CBP and USCG.  It was determined during capability development analysis that the customers faced a maritime information situational awareness gap.  The SA gap was derived from inefficient placement of scarce law enforcement (LE) resources due to lack of actionable information.  For immediate mission impact, analysis results showed that an information fusion engine was needed to provide additional ‘eyes’ to operations centers.  The AoA reflected a lack of a common operating picture (COP) amongst different LE agencies.

### Preferred Alternative

Approach was built around balancing the need for new technology while also using older, existing technology.  The PCSI project undertook a holistic DHS approach versus a parochial component one, interpreting agency specific solutions with the enhanced technology available to address capability gaps & associated threats.  The project takes maximum advantage of partnerships and collaboration for technology development.

The organizations we are collaborating with are:

- JIATF-S

- CBP

- USCG

- US NAVY

- OSD/ATL

- NRO

- U of Texas

- ONI

- LANT/PAC

- NORTHCOM

- SOUTHCOM

### Technical Risks

The technical risks associated with this effort are centered on acquiring the relevant vessel position data from a variety of government and non-government sources to effectively produce a track that is both accurate and timely to the operating agency mission needs.

The data we intend to use is created by others.  All of the data belongs to someone:

  - Original collectors – who collect/create the data.

  - Purchasers – who buy the data from a collector.

  - Recipients – they can be given the data as a partnership.

  - All have caveats on with whom the data can be shared.

A successful PCSI effort (MSA platform) must respect these data rights while serving a diverse user community.

Data volume will become a bottleneck and subsequently is a risk.

The approach to PCSI was built around leveraging technologies initially or already developed by others to minimize risk. PCSI exploits DoD & other agency investments in applicable technology, commercial information sources & leverages those investments to create a DHS capability that can be used by DHS & partner agencies to mitigate defined capability gaps & associated threats. The data rights issue will be minimized by leveraging these existing sources vice developing new data sources that may be redundant.  If unique data is required, then the technology or process to create/acquire that data will be carefully evaluated before investing.

# Project Management

.

## Acquisition Management

### Acquisition Strategy

Government agencies and industry partners were selected to work on PCSI.  Factors for choosing the following performers were based upon demonstrated work experience and subject matter expertise.

Acquisition strategy based on the approved CONOPS for the USCG Interagency Operations Center (IOC).  This aligns the PCSI program with the USCG IOC Acquisition Program.

Performers that are involved are SRI International, NPS, Ocean Power Technology, Naval Research Laboratory, Naval Surface Warfare Center – Crane, SPAWAR System Center Pacific (SSC Pac), Technology Systems, Inc.

### Potential Vendors

Vendors are not required for the transition.

## Scope Management

Scope Management is the process used to document the work required to successfully complete the project. The scope of the project is defined in Section 4.2.1, Work Breakdown Structure, and the processes used to control the scope are defined in Section 4.2.2, Scope Control Plan.

### Work Breakdown Structure

.

| Name | Role | Organization |
| --- | --- | --- |
| Paul Morrisseau | Lead Integrator | SRI International |
| Shane Mason | Lead Architect | SRI International |
| Gerald Bowe | Operations Lead | DHS S&T CTR (CACI) |
| Annie Lum | OMS Lead | NRL |
| TBD | NRL IT Support | NRL |
| Gil Chapman | NRL Analyst | NRL |
| Dave Pollock | SMS Lead | SPAWAR |
| Jeremy Jung | SMS Engineer | SPAWAR |
| Kim Babcock | SME USCG | USCG |

Performer

Technology/System

| Open Mongoose Data Fusion Engine (OMS) | Naval Research Labs (NRL) |
| --- | --- |
| Small Vessel Tracking System (SVTS) | Naval Research Labs (NRL) |
| Flexible Intelligent Stream Tipper (FIST) | Integrity Applications Inc. (IAI) |
| Smart Chart AIS (SC-AIS) | Technology Systems Inc. (TSI) |
|  | ) |
| Homeland Security Information Network (HSIN) | Department of Homeland Security (DHS) |
| Coalition Portal for Situational Awareness (C-PORTS) | Compusult4 |
| National Oceanic And Atmospheric Administration (NOAA) lT Service Catalog | National Oceanic And Atmospheric Administration (NOAA) |
| Department of Homeland Security (DHS) Enterprise Services | Department of Homeland Security (DHS) |
| DoD Data Service Environment (DSE) | Department of Defense (DoD) |
| Government/commercial/public Universal Description Discovery and Integration (UDDI) Registries | Various government, commercial and public entities identified as relevant to enriching situational awareness in the maritime environment |
| Open Mongoose Data Fusion Engine (OMS) | Naval Research Labs (NRL) |

### Scope Control Plan

The PCSI Scope Control Plan reflects a 7 Step process:

| Step |  | Description |
| --- | --- | --- |
| 1 | Request | A request is made for a change to the agreed upon scope baseline. The request may be internally or externally generated, may come in any form, and may have been prompted by any number of reasons or events. |
| 2 | Evaluate | The project manager facilitates an evaluation to confirm that the requested change is in fact a change to the agreed upon scope baseline. If so, the project manager implements the request as described below. |
| 3 | Assess | If the request is in fact a change to the scope baseline, the project manager assesses the impact on project schedule, budget, and work products, using a similar approach as the original project planning process, utilizing team member expertise as needed. |
| 4 | Document | The project manager documents the project impact and other critical information in a change order form. A summary of the change is recorded in a change order log. This log is often not required, but is a very useful tracking device. |
| 5 | Decide | The change order is presented to the project’s governing authority, typically a steering committee or equivalent. In some cases, the project may have a separate change management board to process change requests. The governing authority decides whether or not to implement the change, and obtains approval for any needed additional resources (if it does not itself have the authority to authorize resource changes). |
| 6 | Incorporate | The project manager incorporates changes into the project’s scope baseline in the form of such artifacts as contracts, statements of work, project plans, requirements, and design documents. |
| 7 | Implement | The project team implements the changes. |

## Schedule Management

### Milestones/Deliverables

| Major Project Milestones/Deliverables by Phase | Scheduled Date |
| --- | --- |
| Analysis Phase |  |
| Requirements Approved by Customer | FY 2010 |
| Development Phase |  |
| Inter-related technology efforts integrated into PCSI development efforts. | FY 2010 – FY 2014 |
| Transition Phase |  |
| Integration of OMS track service into CBP AMOC | FY 2014 |

Figure 5: Major Project Milestones and Deliverables by Phase

### Schedule Control Plan

The PM will receive monthly reports detailing the schedule status of work in progress on the contract.  Technical issues and accomplishments will be integrated into the analysis of schedule performance in required reports and as part of Government/contractor meetings.  Reports will reflect integrated cost and schedule reporting and progress against the baseline plan in a manner specified in the SOW. This status reporting may take any form as long as it correlates with true, physical progress on the contract. Schedules that only show the passage of time with no relationship to accomplishment are normally not acceptable (i.e., level-of-effort activities excluded).

The contractor will provide analysis of the most significant schedule variances in a

given period. See Figure 6-7.  The Government PM and the contractor will jointly determine the CWBS and organizational elements that constitute high cost, schedule, and/or technical risk on the contract.

The contractor will provide analysis of these elements if they exceed pre-established cost or

schedule thresholds.  All variances that exceed a certain percentage and/or dollar amount, i.e., all schedule variances that exceed plus or minus x% and plus or minus $x of the cumulative Budgeted Cost for Work Scheduled (BCWS), must be reported. All variances at completion that exceed plus or minus x% will be analyzed.  As part of the status process, the contractor must include an assessment of available resources and capabilities, and provide forecasts that indicate the expected completion date of the effort. The scheduling system should readily display areas where forecast completion dates differ from the planned dates. The contractor must continually reconcile schedule information with performance measurement information.

Scheduling will interface with other planning and control systems to the extent necessary

for measurement and evaluation of contract status. The scheduling system will provide

current status and forecasts of completion dates for authorized work. The contractor's

summary and detailed schedules should enable a comparison of planned and actual status of

program accomplishment based on milestones or other indicators used for control purposes.

## Cost Management

Cost Management is the process used to manage the cost of the project to ensure that actual costs remain within budgeted costs.

### Cost Estimate

Total cost across FY 2013 to 2014 is $5.5 million dollars.

In the analysis towards a cost-estimate, an AoA (Analysis of Alternatives) is performed to:

(1) Identify and evaluate various methods of obtaining needed goods and services,

(2) Determine which alternative is the most advantageous to the Government, and

(3) Document the rationale and analysis for selecting an interagency agreement (IA) as the appropriate acquisition alternative.

In the best procurement approach justification, the break-out costs identified in the funding analysis and Independent Government Cost Estimate (IGCE) have been evaluated by the program office and deemed realistic in terms of the level of effort required for the development and management of this program by the PSCI performers. Based on this rationale, augmented by the analysis provided above, pricing paid to the performers for the proposed IA is hereby determined reasonable and in the best interest of the Government.

### Cost Baseline

| NSWC Crane | SPAWAR | USCG | Naval Research Laboratory | SRI |
| --- | --- | --- | --- | --- |
| $300K | $650K | $195K | $1.3M | $950K |

### Cost Control Plan

An AoA was conducted to address PCSI’s operational effectiveness related to its

life-cycle costs compared to various other alternatives to meet the mission area need

The analysis was intended to:

• Analyze alternatives as part of the process. Alternatives analysis broadly examines

multiple elements of project or program alternatives including technical risk and

maturity, price, and costs. Explicitly analyze continued costs of the baseline. Where appropriate, the analysis shall address the interoperability and commonality of components or systems that are similar in function to other  DHS S&T programs.

• Aid decision makers in judging whether any of the proposed alternatives to an existing

system offers sufficient military and/or economic benefit to justify the cost. For most

systems, the analysis shall consider and baseline against the system(s) that the acquisition program will replace, if they exist. The analysis shall consider the benefits

and detriments, if any, of accelerated and delayed introduction of MDA capabilities,

including the effect on life-cycle costs.

The analysis will largely be quantitative, but qualitative aspects must also be considered.

It facilitates decision makers and staffs at all levels to engage in discussions of key  assumption sand variables, develop better program understanding, and foster joint ownership of the program and program decisions. There shall be a clear linkage between the AoA, system requirements and test and evaluation measures of effectiveness. The analysis shall reveal insights into program knowns and unknowns and highlight relative advantages and disadvantages of the alternatives being considered.

4.5 Status Reporting

An Integrated Master Schedule (IMS) will be used to control all aspects of PCSI program tasks, including monthly status reports.  The PCSI IMS will provide for tracking of detailed tasks and timing of tasks according to the program schedule.

The IMS will also be used for identification of problem area during both program planning and execution.  The IMS schedule will be used as a basis for evaluating changes, and is a significant tool for comparing actual to planned progress.  It will provide performance measurement and evaluate remaining work scope and duration throughout program execution.

# Risk Management

## Risk Management Plan

The PCSI PM has a wide range of supporting data and processes to help them integrate and balance programmatic constraints against risk. The program baseline for each

effort defines the top-level cost, schedule, and technical performance parameters for that

program. Additionally, acquisition planning documents provide detailed

cost, schedule, and technical performance measures for program management efforts.

The objective of this risk management program is to provide a repeatable process for balancing cost, schedule, and performance goals within program funding, especially on programs with designs that approach or exceed the state-of-the-art or have tightly constrained or optimistic cost, schedule, and performance goals.  Success depends on the knowledge gleaned from assessments of all aspects of the program coupled with appropriate mitigations applied to the specific root causes and consequences.

A key concept here is that the customer (CBP & USCG) shares the risk with the development, production, or support contractor (if commercial support is chosen), and does not transfer all risks to the contractor. The PM always has a responsibility to the customer to develop a capable and supportable system and cannot absolve itself of that responsibility. Therefore, all program risks, whether primarily managed by the program office or by the development/support contractor, are of concern and must be assessed and managed by the program office.

Once the PM has determined which risks and how much of each risk to share with the

contractor, it must then assess the total risk assumed by the developing contractor (including

subcontractors). The program office and the developer must work from a common risk

management process and database. Successful mitigation requires that government and the

contractor communicate all program risks for mutual adjudication. Both parties may not always agree on risk likelihoods, and the government PM maintains ultimate approval authority for risk definition and assignment. A common risk database available and open to the government and the contractor is an extremely valuable tool. Risk mitigation involves selection of the option that best provides the balance between performance and cost. It is also possible that throughout the system life cycle there may be an end for different near-term and long-term mitigation approaches. The PCSI risk management process requires a commitment on the part of the PM, the program office and the contractor to be successful. Many impediments exist to risk management implementation, however, the program team must work together to overcome these obstacles.

## Risk Identification and Assessment

Figure 6:  Risk Assessment Values Tables

5

4

3

2

1

1

2

3

4

5

Likelihood

Consequence

Figure 7: Risk Score

| Risk Number | Risk Name | Risk Description | Risk Category | Risk Score | Response Strategy |
| --- | --- | --- | --- | --- | --- |
| 1 | Technical Risk | Detecting small, uncooperative vessels is a difficult challenge. MSTP information fusion system is complex and output sequencing must allow for deliverable actionable intel. | Technical | 2 | Technical risk is partially mitigated by pursuing complementary, but related approaches. The program will focus a significant amount of time, effort, and resources into a full system demo. Intensive SEIPT reviews significantly reduces the project’s technical risk. |
| 2 | Schedule Risk | Schedule risk is low/medium. Estimated time to complete all tasks is based on previous work and similar efforts. There is adequate time to perform the identified tasks. | Schedule | 2 | The project’s schedule is dependent on the available funding. When annual funding levels were reduced, the project schedule was extended to compensate. Similarly, with additional annual funding, the project timeline could be accelerated. Our procurement strategy to select core integrated systems that enables MSTP will significantly reduce schedule risks. |
| 3 | Cost Risk | Cost risk is estimated as medium. Some initial studies and developmental efforts have been combined to save dollars in the near term. The program developmental approach and test bed test and experimentation will insure a very low unit cost, progressively demonstrated during the course of program execution. | Cost | 2 | Our goal is to insure a very low unit cost (both acquisition and operating costs). Without a strong focus on cost, there is little hope for a successful transition of the technology. This risk is being mitigated by clearly communicating to any/all potential technology developers that the end product must be able to be manufactured using traditional microelectronic manufacturing equipment, materials, and processes, thus ensuring inexpensive manufacturing costs. |
| 4 | Business Risk | Business risk is estimated as low/medium. It is anticipated the complexity and production of MSTP will be moderate. Each effort making up PCSI will have a specific function and will be integrated at the systems level to minimize dependencies. System stability will be developed in two phases. First, individual functional subsystems will be rigorously tested in a relevant environment before the design and integration effort to improve functionality and reduce size and cost. | Business | 3 | Business risk is reduced by minimizing dependencies between subsystems as mentioned above. |
| 5 | End user acceptance risk | (Medium): End user acceptance risk is estimated as medium. Success depends upon MSTP integration, transition, and mission results. CBP will most likely have to take a minimal administrative position to assure the integrity of MSTP once the systems are made operational. MSTP is an opportunity for CBP and USCG to apply a valuable technology to detect and intercept un-cooperative small vessel threats. | End user | 1 | Recognizing that the project’s “end-users” are DHS law enforcement agencies, we will continue to develop and communicate a convincing value proposition and business case. To meet the government’s needs (CBP & USCG), the project will demonstrate that the system can make a significant to detect un-cooperative small vessels. |
| 6 | Community Acceptance Risk | Community (defined here as maritime law enforcement agencies) acceptance risk is low/medium. This risk estimate is based on the in-depth understanding of customer requirements and developmental involvement. Extending and synchronizing the capability of primary detection efforts will . | Community acceptance | 1 | In addition to the mitigation strategies discussed above, community acceptance is largely a function of cost incurred, performance, and how seamlessly the technology operates. Most critical to acceptance will be demonstrating the effective detection of uncooperative small vessels with other detected vessels. Ineffective detection capability will discourage use. Incremental experimentation and demonstration will be critical in gaining community acceptance. |

Figure 8: Risk Register